## Activities
Duration (days)
Activity ID | Activity description | Optimistic | Most-Likely | Pessimistic | Predecessor activity
1 | Contract date | 0 | 0 | 0
2 | Financial Close | 0 | 0 | 0
3 | Design | 865 | 920 | 1040 | 1
4 | Obtaining Commencement Certificate | 128 | 130 | 164 | 1
5 | Obtainment of Commencement Certificate | 0 | 0 | 0 | 4,2
6 | Date of commencement | 0 | 0 | 0 | 5
7 | Maintain existing road assets A9 / A1 / A6 | 1194 | 1284 | 1541 | 6
8 | Conditioning, Cables and Conducts, permits | 182 | 200 | 256 | 6
9 | Preload | 363 | 395 | 486 | 6
10 | Construction of new Aqueduct | 234 | 260 | 325 | 6
11 | Construction of the Amsterdam-Rijn Canal bridge | 305 | 335 | 425 | 6
12 | Road works southern A1 lane | 120 | 128 | 155 | 9,10,11
13 | Commissioning of the southern A1 new lane | 0 | 0 | 0 | 12
14 | Producing parts of Railbridge part 1 | 241 | 251 | 279 | 6
15 | Producing parts of Railbridge part 2 | 209 | 220 | 279 | 14
16 | Assembling a railway bridge on location | 667 | 674 | 782 | 14
17 | Moving Railway Bridge in place during Train Free Period | 0 | 0 | 0 | 16
18 | Road works northern A1 lane | 120 | 130 | 147 | 17
19 | Commissioning of the Northern A1 new lane | 0 | 0 | 0 | 18
20 | Road and construction works new part junction Diemen | 519 | 530 | 620 | 13
21 | Build new viaducts A6 | 396 | 400 | 460 | 6
22 | Build second Hollandse bridge | 326 | 340 | 415 | 6
23 | Road and construction works junction Muiderberg | 856 | 930 | 1209 | 6
24 | Road works eastern part A6 | 100 | 100 | 116 | 21, 22
25 | A6 East ready | 0 | 0 | 0 | 24
26 | Reconstruction western part A6 | 380 | 400 | 508 | 25
27 | Commissioning A6 | 0 | 0 | 0 | 18,23,26
28 | Road works existing part Diemen junction | 90 | 90 | 106 | 19,20
29 | Request Availability Certificate | 0 | 0 | 0 | 28
30 | Assess and obtain Availability Certificate | 19 | 20 | 23 | 29
31 | Demolition old A1 (part 1) | 57 | 61 | 71 | 30
32 | Demolition old A1 (part 2) | 29 | 30 | 35 | 31
33 | Greenery for old A1 | 82 | 90 | 107 | 31
34 | Applications and obtaining partial completion certificates | 119 | 120 | 149 | 30
35 | Request Completion Certificate | 0 | 0 | 0 | 33
36 | Assess and obtain Certificate of Completion | 18 | 20 | 24 | 35
37 | Scheduled Completion Date | 0 | 0 | 0 | 36
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D7,0)
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely duration of the activity. The user must define this quantity
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D6,0)

## Mitigations
Mitigation capacity (days)
Mitigation ID | Mitigation measure | Minimum | Most likely | Maximum | Relations | dependency factor (eta) | Objective 1 | Objective 2 | Objective 3
1 | Extra engineering design office personnel | 51 | 52 | 52 | 3 | 0.5 | 2307.6923 | 120000 | 120000
2 | Extra software design capacity | 7 | 7 | 7 | 4 | 0.5 | 4285.7143 | 30000 | 30000
3 | Extra maintenance engineers | 53 | 65 | 65 | 7 | 0.5 | 2307.6923 | 150000 | 150000
4 | Extra administrators for permitting | 22 | 26 | 29 | 8 | 0.5 | 1846.1538 | 48000 | 48000
5 | Applying extra preloading material | 21 | 26 | 26 | 9 | 0.5 | 28846.1538 | 750000 | 750000
6 | Adding extra on site construction flow | 47 | 52 | 55 | 10 | 0.5 | 3846.1538 | 200000 | 200000
7 | Extra prefab construcion capacity | 60 | 65 | 66 | 11 | 0.5 | 2307.6923 | 150000 | 150000
8 | Extra M&E engineers | 26 | 26 | 26 | 12 | 0.5 | 2307.6923 | 60000 | 60000
9 | Extra welding equipment and personnel | 27 | 33 | 33 | 14 | 0.5 | 3030.303 | 100000 | 100000
10 | Extra temporary soil measures | 23 | 26 | 27 | 15 | 0.5 | 9615.3846 | 250000 | 250000
11 | Ancillary on standby | 103 | 104 | 114 | 16 | 0.5 | 1923.0769 | 200000 | 200000
12 | Extra M&E engineers | 7 | 7 | 7 | 18 | 0.5 | 4285.7143 | 30000 | 30000
13 | Extra excavation capacity | 49 | 52 | 52 | 20 | 0.5 | 2403.8462 | 125000 | 125000
14 | Extra concrete workers / carpenters | 42 | 52 | 55 | 21 | 0.5 | 1442.3077 | 75000 | 75000
15 | Temporary ancillary construction and re-work | 36 | 39 | 43 | 22 | 0.5 | 38461.5385 | 1500000 | 1500000
16 | Extra excavation capacity | 31 | 39 | 42 | 23 | 0.5 | 3846.1538 | 150000 | 150000
17 | Extra asphalt equipment and personnel | 52 | 52 | 55 | 26 | 0.5 | 3846.1538 | 200000 | 200000
18 | Extra removal works | 22 | 26 | 27 | 28 | 0.5 | 2884.6154 | 75000 | 75000
19 | Extra equipment and personnel | 5 | 7 | 8 | 30 | 0.5 | 35714.2857 | 250000 | 250000
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (pessimistic) capacity of the mitigation measure. The user must define this quantity.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely capacity of the mitigation measure. The user must define this quantity.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (optimistic) capacity of the mitigation measure. The user must define this quantity.
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This factor defines to what extent the mitigation cost variation depends on the mitigation capacity variation. This factor is between 0 and 1. If this factor is set to 1, then the mitigation cost increases/decreases proportionally to the increase/decrease in he mitigation capacity. If it is set to 0, then the cost will remain constant regardless of the variation in the mitigation capacity. You may set any number between 0 and 1 (i.e., 0.5 means partial relation between the cost variation and the mitigation variation)
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Most-likely cost of the mitigation measure. This is a user input.

## Risks
Risk duration (days)
Risk event ID | Risk event description | Minimum | Most likely | Maximum | Affected activities | Risk probability
1 | Preliminary design rejection, including extra scope of works | 96 | 105 | 119 | 3 | 0.2
2 | EDP audit failure | 13 | 14 | 15 | 4 | 0.05
3 | Existing condition Hollandse Brug deviates from maintenance plan made during tender phase | 63 | 70 | 78 | 7 | 0.15
4 | Unexpected gas conducts | 35 | 35 | 41 | 8 | 0.2
5 | Lower consolidation rate than calculated for | 34 | 35 | 40 | 9 | 0.1
6 | Piling machines break down | 14 | 14 | 15 | 10 | 0.1
7 | Late delivery of prefab elements | 19 | 21 | 25 | 11 | 0.2
8 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 22 | 12 | 0.25
9 | Production equipment failure | 20 | 21 | 23 | 14 | 0.05
10 | Construction site subsides | 13 | 14 | 15 | 15 | 0.05
11 | Ancillary equipment failure | 33 | 35 | 41 | 16 | 0.1
12 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 21 | 18 | 0.25
13 | Discovery of polluted soil | 13 | 14 | 14 | 20 | 0.05
14 | Concrete casting failure | 13 | 14 | 14 | 21 | 0.05
15 | Main pillar subsides | 65 | 70 | 71 | 22 | 0.02
16 | Discovery of polluted soil | 25 | 28 | 32 | 23 | 0.05
17 | Insufficient quality of base layer | 39 | 42 | 47 | 26 | 0.02
18 | Discovery of asphalt with too high PAK percentage | 13 | 14 | 17 | 28 | 0.05
19 | Additional scope of work (misc.) | 130 | 140 | 160 | 30 | 0.01
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (optimistic) delay induced by the risk event. The user must define this quantity.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely delay induced by the risk event. The user must define this quantity.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (pessimistic) delay induced by the risk event. The user must define this quantity.